## Action E - Time_table (hidden)
Action | [5 empty] | 2019 | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023
Action number | Action title | Task | Responsible partner per task | Deliverable | Target | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III
E. Communication and dissemination of results (obligatory)
E.1 | Information and dissemination Reponsible partner for the action: BaltCoasts | 1. Project website and social media accounts | SILAVA | Website | 10,000 hits | 2019 IV: Project website and social media accounts developed and published 2019-12-31; 2020 II: Project webpage update (new article on project progress) 30/06/2020; 2020 IV: Project webpage update (new article on project progress) 30/12/2020; 2021 II: Project webpage update (new article on project progress) 30/06/2021; 2021 IV: Project webpage update (new article on project progress) 30/12/2021; 2022 II: Project webpage update (new article on project progress) 30/06/2022; 2022 IV: Project webpage update (new article on project progress) 30/12/2022; 2023 III: Project webpage update (new article on the project final results) 31/07/2023
|  |  | SILAVA | Social media accounts | Facebook: 200 followers Twitter: 200 followers | 2019 IV: Corporate design and visual identity of the Project developed 2019-12-31; 2020 II: Social media accounts update (new posts on project progress) 30/06/2020; 2020 IV: Social media accounts update (new posts on project progress) 30/12/2020; 2021 II: Social media accounts update (new posts on project progress) 30/06/2021; 2021 IV: Social media accounts update (new posts on project progress) 30/12/2021; 2022 II: Social media accounts update (new posts on project progress) 30/06/2022; 2022 IV: Social media accounts update (new posts on project progress) 30/12/2022; 2023 III: Social media accounts update (new posts on project progress) 31/07/2023
|  | 2. Scientific publications | LUKE | Peer-reviewed journals | 8 scientific publications | 2021 II: 1st Scientific publication on the impact of climate change on GHG emissions from organic soils 2021-06-30; 2022 III: 2nd Scientific publication on carbon inputs and soil carbon stock changes in forests on drained nutrient-rich organic soils 2022-09-01; 2022 IV: 3rd Scientific publication on GHG emission factors for nurtrient-rich organic soils in temperate and hemi-boreal climate zone 2022-12-31
|  | 3. Information and education materials | BALTCOASTS | Informative materials (brochures) | 1,000 coloured copies | 2022 III: Printed project booklet with summaries of main results 2022-09-30
|  |  | BALTCOASTS | Press releases | 10 press releases |  | 1st press release - presentation of the project 30/01/2020 | 2nd press release - "GHG emissions and nutrient-rich organic soils: a twofold relationship" (description of how nutrient-rich organic soils can turn into a net sink but also into a net source of GHG emissions and the important role that they can therefore play in reducing GHG emissions) 31/05/20 |  | 3rd press release - "OrgBalt First National workshops on climate change mitigation measures for nutrient-rich organic soils: implemented action and next steps to be taken." (description of the conference's outcome, ongoing research, objectives and expected results) 31/12/2020 |  | 4th press release - "First CCM measures implemented in demo sites in Latvia and Finland" (summary description of the implemented CCM measures, description of the location and of the soils charactheristics and problems, concluding with expected results and monitoring activities planned. 31/03/2021 | 5th press release "The importance of stakeholders engagement for the success of the LIFE OrgBalt project" (introduction of the PPC model implemented, stakeholders involved and main communication tools planned to inform and involve stakeholders) 30/09/2021 |  |  | 6th press release "Climate change scenarios: how can they effect organic soils" (description of the analysed climate change scenario and the impact they can have on GHG emissions from organic soils as well as on their productivity under traditional land management) 31/05/2022 | 7th press release - "Forest restoration: applied CCM measures within the forest sector" - description of concrete CCM measures implemented in the forestry sector - brief explanation of why CCM measures are important within the forestry sector (forest ageing, deforastation and so on), description of 1/2 already implemented CCM measures, summary of the first measured results and small conclusions on the foreseen future improvements. 30/09/2022 | 8th press release "The economic benefis of CCM measures for nutrient-rich land management practices on farm level" (presentation of the benefits of CCM measures from an economic perspective - summary of the threat of traditional land management pratices and small report on the advantages of climate-smart management practices in the context of farms) 31/12/2022 | 9th press release "OrgBalt Second National workshops on climate change mitigation measures for nutrient-rich organic soils: toward the end of the project" (description of the conference's outcome, conducted researches, research findings and their implication on future land management practices, next steps to be taken, future planned activities) 30/03/2023 |  | 10th press releases on LIFE OrgBalt obtained results and follow up activities. (summary of the project's obtained results and of the replicability and transferability activities planned) 31/08/2023
|  |  | BALTCOASTS | Policy briefs | 5 country specific releases | 2023 III: 5 Policy brief (1 per country LV, EST, LT, DE, FI) summary of the main aspects of the project, actions taken results obtained - provide decision-makers with a background of the main problems and possible solutions 31/08/2023
|  |  | BALTCOASTS | Popular articles | 10 articles |  |  | 1st popular article (summary of the projects' objectives and expected results + current situation on EFs and GHG emissions + CCM situation + a description of the activities that took place so far) 30/03/2020 |  | 2nd popular article "Climate changes: today's and future scenarios" (description of the current and expected impact of climate changes on the LULUCF sector, future threats, actions to be taken) 31/12/2020 | 3rd popular article "The role of soil quality in sustainable growth: best practices on how to tackle the degradation of soils quality" (description of how soil quality can improve soil management and rural development, example of best practices to improve the quality of soils, reduce their degradation in the long term and increase their productivity) 2021-03-30 |  |  | 4th popular article "Agro-forestry, afforestation/reforestation, forest restoration: best practices to increase carbon storage" (general description of possible CCM measures based on the ones implemented in the identified demosites, practical description of the data obtained in at least one demosite, with a focus on the expected impact on socio-economic benefits for the soil productivity and the involved community) 31/12/2021 |  | 5th popular artcicle "Crop rotation: the role of legumes in carbon sequestration enhancement" (Description of the benefit of crop rotation + a practical example of the introduction of legumes in conventional crop rotation in the project demosites) 30/06/2022 | 6th Popular article "Sustainable grassland management techniques: increased productivity and carbon sequestration potential" (presentation of cases from the identified demosite - ex. Of grassland restoration and/or grassland sustainable management - data on GHG emissions before the applied CCM measures and foreseen improvement on GHG emissions in the longterm + a focus should be given to the land improved productivity and the socio-economic return) 30/09/2022 | 7th Popular article "Climate-smart irrigation: land management and water resources" (presentation of cases from the identified demosite - ex. retaining of drainage system, improvement of drainage system - best practices on climate-smart irrigation + a focus should be given to the land improved productivity and socio-economic return) 2022-11-30 | 8th popular article "Cooperation and knowledge exchange best practices: the importance of an integrated approach for a competitive and sustainable rural economy" (introduction on how to develop successful networking and on the advisory centres that can be contacted for support + best practices on networking experiences which could be taken from the PPC model developed within the project but also from RDPs open consultation among stakeholders or from previous engagement activities) 31/03/2023 | 9th popular article "Circular economy, an opportunity for the agricultural sector? Best practices on waste utilisation to reduce waste and emissions" (example of bioeconomy practices such as biofuel and bioplastics or other waste utilisation practices) 30/06/2023 | 10th popular article "Guidelines for the implementation of the simulation model: how to read parameters and how to use the model" (presentation of few study cases including an example of replicability of the model outside the project demo site). 31/08/23
|  |  | BALTCOASTS | Technical articles | 6 articles | 2020 IV: 1st technical articles on Activity data for accounting & Projections of GHG emissions 31/12/20; 2021 II: 2nd technical article on Harmonised methodology for characterisation of peat properties using infrared screening method 30/06/2021; 2022 II: 3rd techincal article on the methodology for the socio-economic analysis of the proposed measures 30/06/2022; 2022 IV: 4th technical article on methodologies improvement for GHG inventory and impact on related national reports 31/12/2022; 2023 I: 5th technical article on the development of the default parameters for calculations of efficiency of the climate change mitigation measures 30/03/2023; 2023 III: 6th technical article on the methodology for the application of the Simulation tool in real life conditions 31/08/2023
|  |  | BALTCOASTS | Articles for general public | 10 articles / interviews |  |  |  | 1st article for the general public "The OrgBalt project from a practical perspective" (a summary of the project with a focus on practical explanations and interviews to explain the objectives of the project, different demo sites identified and their characteristics) 30/09/2020 | 2nd article for the general public "Climate changes and land management" (description of the possible effects of climate changes on land management and on the rural economy and the possible consequences on the society as a whole + actions to be taken) 31/12/2020 | 3rd article for the general public "GHG emissions and nutrient-rich organic soils: a twofold relationship" (description of how nutrient-rich organic soils can turn into a net sink but also into a net source of GHG emissions and the important role that they can therefore play in reducing GHG emissions) 31/03/2021 |  | 4th article for the general public "Climate-smart land management: the importance of the cooperation among all the involved actors" (which are the actors involved in land management and in particular in the project, which actions have been taken to enhance their cooperation, which actions have been taken to improve their expertise) 31/07/2021 | 5th article for the general public "The role of forests in a changing climate" (why is it important to preserve forests, how are they changing, how can we better understand them, forests and their role for communities, actors involved, series of practical cases of CCM measures and interviews - forest sector - ) 31/12/2021 | 6th article for the general public "The role of cropland in a changing climate" (why is it important to sustainably manage croplands, how can technology improve their productivity, how are they changing, , what's their role for communities, which are the actors involved, series of practical cases of CCM measures and interviews - cropland sector) 31/03/2022 | 7th article for the general public "The role of grassland in a changing climate" (why is it important to sustainably manage grasslands, how can technology improve their productivity, how are they changing, , what's their role for communities, which are the actors involved, series of practical cases of CCM measures and interviews - grassland sector) 30/06/2022 | 8th article for the general public "The role of peatland in a changing climate" (why is it important to sustainably manage peatlands, how can technology improve their productivity, how are they changing, what's their role for communities, which are the actors involved, series of practical cases of CCM measures and interviews - peatland sector) 30/09/2022 |  | 9th article for the general public "The socio-economic benefits of CCM measures: a comparison between traditional and future land management practices and their productivity in the long term" (why traditional land management is no longer sustainable, future economic threats, economics of CCM measures in the long term) 31/03/2023 |  | 10th article for the general public "The OrgBalt project: let's sum up" (a summary of the project's results in the identified demo sites, with a focus on practical explanations and interviews to explain the results of the project and the next steps to be taken) 31/08/2023
|  |  | BALTCOASTS | 3 short films (up to 10-12 min.) | Audience: up to 100,000 | 2020 IV: 1st short documentary about the OrgBalt project (presentation of the project, partners, sites involved, objectives and expected results) 31/12/2020; 2021 II: 2nd short documentary about climate change with a focus on nutrient-rich organic soils contribution to GHG emissions. "Climate change and GHG emissions in nutrient-rich organic: why do we need to do something" 30/06/2021; 2022 II: 3rd short documentary about CCM measures implementation in sample demo sites within the forest sector (showing concrete demo sites and involved stakeholders when possible) "Restoring forests: climate-smart management approaches within the forest sector" (deliverable deadline 01-07-2021) 30/06/2022; 2023 II: 4th short documentary about improvements in GHG emissions and CO2 removals due to cropland and grassland management (showing concrete demo sites and involved stakeholders when possible) "The role of cropland and grassland management in GHG emissions improvement and CO2 removals: successful stories." (deliverable deadline 01-07-2021) 30/06/2023
|  |  | BALTCOASTS | E-Newsletter | 8 newsletters | 2020 I: 1st newsletter "The OrgBalt project: an introduction" (summary of the projects' objectives and expected results + involved actors + a description of the activities that took place so far) 30/03/2020; 2020 III: 2nd newsletter "Report on the 1st national Workshop" (progress report concluded /presentation of the list of demo sites + results of the first National workshops on CCM / data on websites and SN if available) 30/09/2020; 2021 I: 3rd newsletter "The role of forests in a changing climate" (first results obtained in the forest sectors, initiatives organized, demo sites involved, next steps) 30/03/2021; 2021 III: 4th newsletter "The role of cropland in a changing climate" (first results obtained in the cropland sectors, initiatives organized, demo sites involved, next steps) 30/09/2021; 2022 I: 5th newsletter "The role of grassland in a changing climate" (first results obtained in the grassland sectors, initiatives organized, demo sites involved, next steps) 30/03/2022; 2022 III: 6th newsletter "The project educational and informative objective" (education events organised, information and exchaneg opportunities organised) 31/08/2022; 2023 I: 7th newsletter "Report on the 2nd National Workshop" (toward the end of the project, obtained results, next steps to be taken) 30/03/2023; 2023 III: 8th newsletter - project's final results, replicability and transferability plan, an general overview of the LIFE key performance indicators reached. 31/08/23
|  | 4. Layman's report | BALTCOASTS | Layman's report | 1 to be widely disseminated | 2023 III: Layman`s report 2023-08-31
|  | 5. Notice boards and information signs | BALTCOASTS | Notice boards & Information signs | undefined / 17 information signs | 2019 IV: Notice boards / Information signs 2019-12-31
E.2 | Dissemination and training events Reponsible partner for the action: BaltCoasts | 1. Planning and organization of national workshops | MA | National workshops | 2 different target groups events per country | 2020 IV: First National workshops on climate change mitigation measures for nutrient-rich organic soils held (to present the first project results, the identified demo sites and the next activities to come (involvement of all stakeholders levels) 2020-12-31 08/12/2020; 2023 I: Second National workshops on climate change mitigation measures for nutrient-rich organic soils held (involvement of all stakeholders levels) 2023-03-31
|  | 2. Organisation of a Final internationa conference | BALTCOASTS | Final international conference | 1 conference | 2023 III: Final international conference held 2023-07-31
|  | 3. Planning and organisation of the information and dissemination events | BALTCOASTS | External events | 7 events | bar: 2021 I
|  |  | BALTCOASTS | Educational events | 6 events | bar: 2021 I
E.3 | Networking Reponsible partner for the action: Luke | 1. Identification of relevant projects and networks, exchange of experience | LUKE | Thematic Workgroup | 1 | 2021 II: 1st Thematic workgroup (meetings once every four months to discuss the project progress and results and in particular the advance in the development of GHG inventories). 30/06/2021; 2021 IV: 2nd Thematic workgroup (meetings once every four months to discuss the project progress and results and in particular the advance in the development of GHG inventories). 31/10/2021; 2022 I: 3rd Thematic workgroup (meetings once every four months to discuss the project progress and results and in particular the advance in the development of GHG inventories). 28/02/2022; 2022 III: 4th Thematic workgroup (meetings once every four months to discuss the project progress and results and in particular the advance in the development of GHG inventories). 31/07/2022; 2022 IV: 5th Thematic workgroup (meetings once every four months to discuss the project progress and results and in particular the advance in the development of GHG inventories). 31/12/2022; 2023 II: 6th Thematic workgroup (meetings once every four months to discuss the project progress and results and in particular the advance in the development of GHG inventories). 01/05/2023; 2023 III: 7th Thematic workgroup (meetings once every four months to discuss the project progress and results and in particular the advance in the development of GHG inventories). 30/08/2023
|  |  | LUKE | Networking workshops at national level | several - during the whole project | bar: 2021 I
|  |  | LUKE | Experience exchange visits | two three-days visits | 2022 I: Experience exchange meeting - CCM measures implementation: a discussion (first results, stakeholder respond) 31/03/2022; 2023 I: Experience exchange meeting - CCM measures implementation: a discussion (toward the end of the project, what's next) 31/01/2023
|  |  | LUKE | Networking with similar international projects | 3 already identified , other to be added | 2019 IV: LIFE ghgTASE (coord. Luke) SNS-120 (coord. Luke) LIFE14 CCM/FI/000254 “OPAL-Life” Optimising Agricultural Land Use to Mitigate Climate Change (coord. Luke)
|  | 2. Elaboration of a Joint Action Program | LUKE | Joint Baltic and Finnish Action Program | n/a | 2023 III: Joint Baltic and Finnish Climate Change Mitigation Actio Program Establisfed 2023-08-31
Note on G4: Adelaide: do we have some statistics?
Note on G5: Adelaide: is it completed?
Note on G16: Adelaide: are they all in place?

## E1-3 Activities timetable
ACTION | TASK | Responsible partner per task | DELIVERABLE | KEY TARGET | Implementation | DEADLINE in project | TIMETABLE | Related activity
E.1 Information and dissemination | 1. Project website and social media accounts | SILAVA | Website | 10,000 hits | orgbalt.eu | 31/12/2019 | IV 2019 II, IV 2020 II, IV 2021 II, IV 2022 III 2023 | n/a
|  | SILAVA | Social media accounts | Facebook: 200 followers Twitter: 200 followers | https://www.facebook.com/orgbalt/ https://twitter.com/orgbalt https://www.instagram.com/orgbalt/ (not implemented yet) | 31/12/2019 | IV 2019 II, IV 2020 II, IV 2021 II, IV 2022 III 2023 | n/a
| 2. Scientific publications | LUKE | Peer-reviewed journals | 8 scientific publications | Scientific publication on the impact of climate change on GHG emissions from organic soils | 2021-06-30 | 2021-06-30 | C.2. Tools for modelling the impact of climate change on GHG emissions
[5 empty] | Scientific publication on carbon inputs and soil carbon stock changes in forests on drained nutrient-rich organic soils | 2022-09-01 | 2022-09-01 | C.1. Filling knowledge gaps on GHG emissions from organic soils
[5 empty] | Scientific publication on GHG emission factors for nurtrient-rich organic soils in temperate and hemi-boreal climate zone | 2022-12-31 | 2022-12-31 | C.1. Filling knowledge gaps on GHG emissions from organic soils
[5 empty] | 4th will be specified |  | Deadline of acion E1 31.08.2023
5th will be specified
6th will be specified
7th will be specified
8th will be specified
| 3. Information and education materials | BALTCOASTS | Informative materials (brochures) (ENG and all national languague) | 1,000 coloured copies | Printed project booklet on GHG emissions’ mitigation measures and with summaries of main results | 2022-09-30 | 2022-09-30
|  | BALTCOASTS | Press releases | 10 press releases | 1st press release - presentation of the project | 31/08/2023 | 2020-01-30
[5 empty] | 2nd press release - "GHG emissions and nutrient-rich organic soils: a twofold relationship" (description of how nutrient-rich organic soils can turn into a net sink but also into a net source of GHG emissions and the important role that they can therefore play in reducing GHG emissions) | 31/08/2023 | 2020-05-31 | C.1. Filling knowledge gaps on GHG emissions from organic soils
[5 empty] | 3rd press release - "Climate-smart organic soil management practices" (Also information about First National workshops, already implemented action and next steps to be taken.description of ongoing research, some already acheived resullts) | 31/08/2023 | 2020-12-31 | C.1. Filling knowledge gaps on GHG emissions from organic soils
[5 empty] | 4th press release - "First CCM measures implemented in demo sites" (summary description of the implemented CCM measures, description of the location and of the soils charactheristics and problems, concluding with expected results and planned monitoring activities. | 31/08/2023 | 2021-03-31 | C.3. Implementation of climate chaneg mitigation measures in selected demo sites
[5 empty] | 5th press release "The importance of public-privat cooperation" (introduction of the PPC model implemented, stakeholders involved and main communication tools planned to inform and involve stakeholders) | 31/08/2023 | 2021-09-30 | C.4. Strategies and action plans
[5 empty] | 6th press release "Climate change scenarios: how can they effect organic soils" (description of the analysed climate change scenario and the impact they can have on GHG emissions from organic soils as well as on their productivity under traditional land management) | 31/08/2023 | 2022-05-31 | C.2. Tools for modelling the impact of climate change on GHG emissions
[5 empty] | 7th press release - "Forest restoration: applied CCM measures within the forest sector" - description of concrete CCM measures implemented in the forestry sector - brief explanation of why CCM measures are important within the forestry sector (forest ageing, deforastation and so on), description of 1/2 already implemented CCM measures, summary of the first measured results and small conclusions on the foreseen future improvements. | 31/08/2023 | 2022-09-30 | C.3. Implementation of climate chaneg mitigation measures in selected demo sites
[5 empty] | 8th press release "The economic benefis of CCM measures for nutrient-rich land management practices on farm level" (presentation of CCM measures benefit from an economic perspective - summary of the threat of traditional land management pratices and small report on the advantages of climate-smart management practices in the context of farms) | 31/08/2023 | 2022-12-31 | C.4. Strategies and action plans
[5 empty] | 9th press release "…..." (description of the conference's outcome, conducted researches, research findings and their implication on future land management practices, next steps to be taken, future planned activities) | 31/08/2023 | 2023-03-30 | C.1. Filling knowledge gaps on GHG emissions from organic soils
[5 empty] | 10th press releases on LIFE OrgBalt obtained results and follow up activities. (summary of the project's obtained results and of the replicability and transferability activities planned) | 31/08/2023 | 2023-08-31 | D.1. Monitoring of the implementation of project activities; D.2. Monitoring the socio-economic impact of the Project actions; D.3. Monitoring and measuring the LIFE key performance indicators
|  | BALTCOASTS | Policy briefs (ENG and national languages) | 5 country specific releases (one per country) | 5 Policy briefs (1 per country LV, EST, LT, DE, FI) summary of the main aspects of the project, actions taken results obtained - provide decision-makers with a background of the main problems and possible solutions | 31/08/2023 | 2023-08-31 | D.1. Monitoring of the implementation of project activities; D.2. Monitoring the socio-economic impact of the Project actions; D.3. Monitoring and measuring the LIFE key performance indicators
|  | BALTCOASTS | Popular articles (ENG and optional in national languages) | 10 articles | 1st popular article (summary of the projects' objectives and expected results + current situation on EFs and GHG emissions + CCM situation + a description of the activities that took place so far) | 31/08/2023 | 2020-03-30 | D.1. Monitoring of the implementation of project activities: C.1. Filling knowledge gaps on GHG emissions from organic soils
[5 empty] | 2nd popular article "Climate changes: today's and future scenarios" (description of the current and expected impact of climate changes on the LULUCF sector, future threats, actions to be taken) | 31/08/2023 | 2020-12-31 | C.2. Tools for modelling the impact of climate change on GHG emissions
[5 empty] | 3rd popular article "The role of soil quality in sustainable growth: best practices on how to tackle the degradation of soils quality" (description of how soil quality can improve soil management and rural development, example of best practices to improve the quality of soils, reduce their degradation in the long term and increase their productivity) | 31/08/2023 | 2021-03-30 | C.4. Strategies and action plans
[5 empty] | 4th popular article "Agro-forestry, afforestation/reforestation, forest restoration: best practices to increase carbon storage" (general description of possible CCM measures based on the ones implemented or to be implemented in the identified demosites, practical description of the data obtained in at least one demosite (if possible), with a focus on the expected impact on socio-economic benefits for the soil productivity and the involved community) | 31/08/2023 | 2021-12-31 | C.3. Implementation of climate change mitigation measures in selected demo sites C.4. Strategies and action plans
[5 empty] | 5th popular artcicle "Crop rotation: the role of legumes in carbon sequestration enhancement" (Description of the benefit of crop rotation + a practical example of the introduction of legumes in conventional crop rotation in the project demosites) | 31/08/2023 | 2022-06-30 | C.3. Implementation of climate change mitigation measures in selected demo sites C.4. Strategies and action plans
[5 empty] | 6th Popular article "Sustainable grassland management techniques: increased productivity and carbon sequestration potential" (presentation of cases from the identified demosite - ex. Of grassland restoration and/or grassland sustainable management - data on GHG emissions before the applied CCM measures and foreseen improvement on GHG emissions in the longterm + a focus should be given to the land improved productivity and the socio-economic return) | 31/08/2023 | 2022-09-30 | C.3. Implementation of climate change mitigation measures in selected demo sites C.4. Strategies and action plans
[5 empty] | 7th Popular article "Climate-smart irrigation: land management and water resources" (presentation of cases from the identified demosite - ex. retaining of drainage system, improvement of drainage system - best practices on climate-smart irrigation + a focus should be given to the land improved productivity and socio-economic return) | 31/08/2023 | 2022-11-30 | C.3. Implementation of climate change mitigation measures in selected demo sites C.4. Strategies and action plans
[5 empty] | 8th popular article "Cooperation and knowledge exchange best practices: the importance of an integrated approach for a competitive and sustainable rural economy" (introduction on how to develop successful networking and on the advisory centres / institutions / organisations that can be contacted for support + best practices on networking experiences which could be taken from the PPC model developed within the project but also from RDPs open consultation among stakeholders or from previous engagement activities) | 31/08/2023 | 2023-03-31 | C.4. Strategies and action plans
[5 empty] | 9th popular article "Circular economy, an opportunity for the agricultural sector? Best practices on waste utilisation to reduce waste and emissions" (example of bioeconomy practices such as biofuel and bioplastics or other waste utilisation practices) | 31/08/2023 | 2023-06-30 | C.4. Strategies and action plans
[5 empty] | 10th popular article "Guidelines for the implementation of the simulation model: how to read parameters and how to use the model" (presentation of few study cases including an example of replicability of the model outside the project demo site). | 31/08/2023 | 2023-08-31 | C.5. Replicability tools
|  | BALTCOASTS | Technical articles (to put only in project (and partners) webpage) (ENG and optional in national languages) | 6 articles | 1st technical articles on Activity data for accounting & Projections of GHG emissions | 31/08/2023 | 2020-12-31 | C.1. Filling knowledge gaps on GHG emissions from organic soils
[5 empty] | 2nd technical article on Harmonised methodology for characterisation of peat properties using infrared screening method | 31/08/2023 | 2021-06-30 | C.2. Tools for modelling the impact of climate change on GHG emissions
[5 empty] | 3rd technical article on the methodology for the socio-economic analysis of the proposed measures | 31/08/2023 | 2022-06-30 | C.2. Tools for modelling the impact of climate change on GHG emissions
[5 empty] | 4th technical article on methodologies improvement for GHG inventory and impact on related national reports | 31/08/2023 | 2022-12-31 | C.2. Tools for modelling the impact of climate change on GHG emissions
[5 empty] | 5th technical article on the development of the default parameters for calculations of efficiency of the climate change mitigation measures | 31/08/2023 | 2023-03-30 | C.5. Replicability tools
[5 empty] | 6th technical article on the methodology for the application of the Simulation tool in real life conditions | 31/08/2023 | 2023-08-31 | C.5. Replicability tools
|  | BALTCOASTS | Articles for general public (project homepage, project partners wbpages) (ENG and optional in national languages) | 10 articles / interviews | 1st article for the general public "The OrgBalt project from a practical perspective" (a summary of the project with a focus on practical explanations and interviews to explain the objectives of the project, to present the different demo sites identified and their characteristics) | 31/08/2023 | 2020-09-30 | D.1. Monitoring of the implementation of project activities
[5 empty] | 2nd article for the general public "Climate changes and land management" (description of the possible effects of climate changes on land management and on the rural economy and the possible consequences on the society as a whole + actions to be taken) | 31/08/2023 | 2020-12-31 | C.2. Tools for modelling the impact of climate change on GHG emissions
[5 empty] | 3rd article for the general public "GHG emissions and nutrient-rich organic soils: a twofold relationship" (description of how nutrient-rich organic soils can turn into a net sink but also into a net source of GHG emissions and the important role that they can therefore play in reducing GHG emissions) | 31/08/2023 | 2021-03-31 | C.1. Filling knowledge gaps on GHG emissions from organic soils
[5 empty] | 4th article for the general public "Climate-smart land management: the importance of the cooperation among all the involved actors" (which are the actors involved in land management and in particular in the project, which actions have been taken to enhance their cooperation, which actions have been taken to improve their expertise) | 31/08/2023 | 2021-07-31 | C.4. Strategies and action plans
[5 empty] | 5th article for the general public "The role of forests in a changing climate" (why is it important to preserve forests, how are they changing, how can we better understand them, forests and their role for communities, actors involved, series of practical cases of CCM measures and interviews - forest sector - ) | 31/08/2023 | 2021-12-31 | C.3. Implementation of climate change mitigation measures in selected demo sites C.4. Strategies and action plans
[5 empty] | 6th article for the general public "The role of cropland in a changing climate" (why is it important to sustainably manage croplands, how can technology improve their productivity, how are they changing, , what's their role for communities, which are the actors involved, series of practical cases of CCM measures and interviews - cropland sector) | 31/08/2023 | 2022-03-31 | C.3. Implementation of climate change mitigation measures in selected demo sites C.4. Strategies and action plans
[5 empty] | 7th article for the general public "The role of grassland in a changing climate" (why is it important to sustainably manage grasslands, how can technology improve their productivity, how are they changing, , what's their role for communities, which are the actors involved, series of practical cases of CCM measures and interviews - grassland sector) | 31/08/2023 | 2022-06-30 | C.3. Implementation of climate change mitigation measures in selected demo sites C.4. Strategies and action plans
[5 empty] | 8th article for the general public "The role of peatland in a changing climate" (why is it important to sustainably manage peatlands, how can technology improve their productivity, how are they changing, what's their role for communities, which are the actors involved, series of practical cases of CCM measures and interviews - peatland sector) | 31/08/2023 | 2022-09-30 | C.3. Implementation of climate change mitigation measures in selected demo sites C.4. Strategies and action plans
[5 empty] | 9th article for the general public "The socio-economic benefits of CCM measures: a comparison between traditional and future land management practices and their productivity in the long term" (why traditional land management is no longer sustainable, future economic threats, economics of CCM measures in the long term) | 31/08/2023 | 2023-03-31 | C.4. Strategies and action plans
[5 empty] | 10th article for the general public "The OrgBalt project: let's sum up" (a summary of the project's results in the identified demo sites, with a focus on practical explanations and interviews to explain the results of the project and the next steps to be taken) | 31/08/2023 | 2023-08-31 | D.1. Monitoring of the implementation of project activities
|  | BALTCOASTS | 4 short films (up to 7-8 min.) (ENG with subtitles in national languages) | Audience: up to 100,000 | 1st short documentary about the OrgBalt project (presentation of the project, partners, sites involved, objectives and expected results) "The Orgbalt project: research and land management together to respond to the challenge of climate change" | 01/07/2021 | 2020-12-31 | C.1. Filling knowledge gaps on GHG emissions from organic soils D.1. Monitoring of the implementation of project activities
[5 empty] | 2nd short documentary about climate change with a focus on nutrient-rich organic soils contribution to GHG emissions. "Climate change and GHG emissions in nutrient-rich organic: why do we need to do something" | 01/07/2021 | 2021-06-30 | C.2. Tools for modelling the impact of climate change on GHG emissions
[5 empty] | 3rd short documentary about CCM measures implementation in sample demo sites within the forest sector (showing concrete demo sites and involved stakeholders when possible) "Restoring forests: climate-smart management approaches within the forest sector" | 01/07/2021 | 30/06/2022 (prolongation need to be accepted from EU) | C.3. Implementation of climate change mitigation measures in selected demo sites
[5 empty] | 4th short documentary about improvements in GHG emissions and CO2 removals due to cropland and grassland management (showing concrete demo sites and involved stakeholders when possible) "The role of cropland and grassland management in GHG emissions improvement and CO2 removals: successful stories." | 01/07/2021 | 30/06/2023 (prolongatio need to be accepted from EU) | C.3. Implementation of climate change mitigation measures in selected demo sites
|  | BALTCOASTS | E-Newsletter (ENG and national languages) | 8 newsletters | 1st newsletter "The OrgBalt project: an introduction" (summary of the projects' objectives and expected results + involved actors + a description of the activities that took place so far) | 31/08/2023 | 2020-03-30 | D.1. Monitoring of the implementation of project activities
[5 empty] | 2nd newsletter "Report on the 1st national Workshop" (progress report / presentation of the list of demo sites + results of the first National workshops on CCM / data on websites and SN if available) | 31/08/2023 | 2020-09-30 | D.1. Monitoring of the implementation of project activities C.1. Filling knowledge gaps on GHG emissions from organic soils
[5 empty] | 3rd newsletter "The role of forests in a changing climate" (first results obtained in the forest sectors, initiatives organized, demo sites involved, next steps, study visits) | 31/08/2023 | 2021-03-30 | C.3. Implementation of climate change mitigation measures in selected demo sites C.4. Strategies and action plans
[5 empty] | 4th newsletter "The role of cropland in a changing climate" (first results obtained in the cropland sectors, initiatives organized, demo sites involved, next steps, study visits) | 31/08/2023 | 2021-09-30 | C.3. Implementation of climate change mitigation measures in selected demo sites C.4. Strategies and action plans
[5 empty] | 5th newsletter "The role of grassland in a changing climate" (first results obtained in the grassland sectors, initiatives organized, demo sites involved, next steps, study visits) | 31/08/2023 | 2022-03-30 | C.3. Implementation of climate change mitigation measures in selected demo sites C.4. Strategies and action plans
[5 empty] | 6th newsletter "The project educational and informative objectives" (education events organised, information and exchange opportunities organised) | 31/08/2023 | 2022-08-31 | C.1. Filling knowledge gaps on GHG emissions from organic soils
[5 empty] | 7th newsletter "Report on the 2nd National Workshop" (toward the end of the project, obtained results, next steps to be taken) | 31/08/2023 | 2023-03-30 | C.1. Filling knowledge gaps on GHG emissions from organic soils D.1. Monitoring of the implementation of project activities
[5 empty] | 8th newsletter - project's final results, replicability and transferability plan, an general overview of the LIFE key performance indicators reached. | 31/08/2023 | 2023-08-31 | D.1. Monitoring of the implementation of project activities; D.2. Monitoring the socio-economic impact of the Project actions; D.3. Monitoring and measuring the LIFE key performance indicators
| 4. Layman's report | BALTCOASTS | Layman's report (ENG and national languages) | 1 to be widely disseminated | Layman's report: presentation of the Project backgrounds, objectives, actions and results in a simple and comprehensible way | 31/08/2023 | 2023-05-31 | D.1. Monitoring of the implementation of project activities; D.2. Monitoring the socio-economic impact of the Project actions; D.3. Monitoring and measuring the LIFE key performance indicators
| 5. Notice boards and information signs | BALTCOASTS | Notice boards, Information signs (National languages and ENG) | Notice boards acording to N of demo sites | Location, date | 31/12/2019 | 2019-12-31 | D.1. Monitoring of the implementation of project activities
E.2 Dissemination and training events | 1. Planning and organization of national workshops | MA | National workshops | 2 events per country | First National workshops | 2020-06-30 | 2020-06-30
[5 empty] | Second National workshops | 2023-03-31 | 2023-03-31
|  |  | Training workshops | 2 events per country | First phase |  | 2020-12-31
[5 empty] | Second phase |  | 2023-03-31
| 2. Organisation of a Final international conference | BALTCOASTS | Final international conference | 1 conference | Innovative solutions for reduction of GHG emissions from organic soils | 2023-07-31 | 2023-05-31
| 3. Planning and organisation of the information and dissemination events | BALTCOASTS | External events (presenttion or poster) | 7 events | Presentation of the project and results in different events organized by third parties | 31/08/2022 | 2020-09-30
|  | BALTCOASTS | Educational events | 6 events | Educational events addressed to Higher Education Institutions students | 31/05/2023 | 2023-05-31
E.3 Networking | 1. Identification of relevant projects and networks, exchange of experience | LUKE | Thematic Workgroup | n/a | Thematic workgroup (meetings once every four months to discuss the project progress and results and in particular the advance in the development of GHG inventories). | n/a | several dates | C.4. Strategies and action plans
|  | LUKE | Networking with similar international projects | 3 already identified in project proposal, other to be added | LIFE ghgTASE | ongoing | ongoing | C.1. Filling knowledge gaps on GHG emissions from organic soils
SNS-120
LIFE14 CCM/FI/000254 “OPAL-Life” Optimising Agricultural Land Use to Mitigate Climate Change
Anthropogenic greenhouse gas emissions from organic forest soils: improved inventories and implications for sustainable management (SNS-120)
Optimising Agricultural Land Use to Mitigate Climate Change (OPAL-Life)
New management practices in planting and management of arable fields and forests on organic soils – methods for stable bioeconomies to mitigate climate change (SOMPA)
Climate smart management practices on Norwegian organic soils (MYR)
Wise use of drained peatlands in a bio-based economy: development of improved assessment practices and sustainable techniques for mitigation of greenhouse gases (PEATWISE)
Towards sustainable peatland forestry - solutions for economic and ecological challenges (SuoPPP)
Towards Carbon Neutral Municipalities and Regions (CANEMURE)
Climate change mitigation in organic soils on cattle farms (COSCA)
|  | LUKE | Experience exchange visits | two three-days visits (a selected internal group of three project's implementers) | to be defined | 31/01/2023 | 2023-01-31
[5 empty] | to be defined | 31/01/2023 | 2023-01-31
| 3. Elaboration of a Joint Action Program | LUKE | Joint Baltic and Finnish Action Program | n/a | Joint Baltic and Finnish Climate Change Mitigation Actio Program Establisfed | 31/08/2023 | 2023-08-31